## Feuil1
Daily Scrum | Time | Location | Attendees | Agenda | Discussion
October 3rd, 2024 | 4:15pm - 4:30pm | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Go over user stories and tasks | During this meeting, we reviewed the user stories and tasks currently in progress. We ensured that each team member had a clear understanding of their responsibilities and the next steps for the project.
October 5th, 2024 | 11:00am - 11:15:am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Input validation 2) Table creation for courses and teams | In this meeting, we focused on updating the input validation for account creation on both the frontend and backend. Additionally, we created a table for courses and updated the functionality so that teams could be attached to a course, streamlining the data structure for future use.
October 7th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1)UI design for students' view | We began work on the UI design for the students’ view, focusing on creating an intuitive layout to improve user experience. The team discussed initial design choices and planned further enhancements.
October 8th, 2024 | 12:00pm - 12:15pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Teams API 2) User verification logic | We worked on creating the Teams API and successfully added tests for the functionality. In addition, we implemented some logic for user verification to ensure that only authorized users can perform specific actions within the system.
October 9th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Fetch module clarification 2) Project modifications | We discussed the fetch module and clarified its usage within the project. Additionally, we decided to remove the username field from the project as it was no longer necessary based on the updated requirements.
October 11th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Continuation of UI design for students' view | We continued refining the UI design for the students’ view, finalizing adjustments to make the layout more user-friendly. The team ensured alignment on the design vision and began preparations for implementation.
October 13th, 2024 | 1:00pm - 1:15pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Backend and frontend updates | During this meeting, we worked on backend endpoints to retrieve courses and further developed the teams page. We also reviewed a pull request to ensure that the changes aligned with the project requirements.
October 14th-15th, 2024 | 30 minutes | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Instructor’s student list 2) CSV upload page | We focused on implementing the instructor’s student list functionality and worked on the frontend CSV upload page. Additionally, we clarified the team information that should be sent to the frontend and enforced database rules to ensure that each student is part of only one team.
October 16th-17th, 2024 | 30 minutes | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Course selection 2) Team CRUD | We began working on course selection functionality and continued developing the team CRUD (Create, Read, Update, Delete) features. In addition, we fixed bugs and implemented course selection binding, along with logic for student views. Acceptance tests were performed for the login and registration processes, and we started working on teammate evaluation UI and logic.
October 18th, 2024 | 10:00am - 10:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) API learning 2) UI design for team creation | We continued learning about APIs and worked together to help improve the UI design of the CSV drag and drop feature. Progress was also made on the design of the team creation page.
October 19th, 2024 | 4:15pm - 4:30pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Pull request merging 2) Test fixes | We focused on merging pending pull requests and fixing issues with existing tests. Additionally, we reviewed what tasks remained for the sprint and aligned team members on priorities to ensure all critical items are addressed.
October 21st, 2024 | 11:00am-11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Team creation page 2) CI pipeline debugging | The team continued working on the team creation page, refining the design and implementation. We also dedicated time to debugging the CI pipeline to improve its stability and efficiency for ongoing development needs.
October 22nd-23rd, 2024 | 30 minutes | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Evaluations endpoints 2) Members page implementation | During these meetings, we completed the evaluations endpoints and reviewed multiple pull requests. We helped debug some issues and finished the implementation of the members page, connecting it to the necessary APIs. The CSV upload page was also connected to the backend successfully.
October 24th, 2024 | 4:20pm - 4:35pm | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Task separation and sprint planning | We discussed the separation of tasks for the remaining work in the sprint. We also talked about how to use context effectively, the grading structure, and the timing of the tasks. Each team member committed to completing their assigned tasks by the end of the sprint.