## Feuil1
Daily Scrum | Time | Location | Attendees | Agenda | Discussion | Important note
October 3rd, 2024 | 4:15pm - 4:30pm | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Go over user stories and tasks | During this meeting, we reviewed the user stories and tasks currently in progress. We ensured that each team member had a clear understanding of their responsibilities and the next steps for the project.
October 4rd, 2024 | NO MEETING
October 5th, 2024 | 11:00am - 11:15:am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Input validation 2) Table creation for courses and teams | The team reviewed recent updates to input validation for account creation, addressing any outstanding issues. We also discussed the approach for organizing data tables for courses and teams to ensure clarity and maintainability in the project structure.
October 6th, 2024 | NO MEETING
October 7th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1)UI design for students' view | We discussed initial design ideas for the students’ view interface, focusing on layout and user experience considerations. Feedback was shared on each design approach, and we outlined next steps for creating a cohesive look.
October 8th, 2024 | 12:00pm - 12:15pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Teams API 2) User verification logic | We discussed the progress of the Teams API, including the approach to testing and verifying it. Additionally, the team deliberated on the best approach to implementing user verification to ensure secure data handling.
October 9th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Fetch module clarification 2) Project modifications | The team discussed the functionality and use cases of the fetch module in our project. We also reviewed the decision to remove usernames to simplify the database structure and reduce redundancy.
October 10th, 2024 | NO MEETING
October 11th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Continuation of UI design for students' view | We finalized the design choices for the students' view UI, discussing adjustments to ensure the interface was both user-friendly and aligned with our initial vision. We agreed on key elements to focus on during implementation.
October 12th, 2024 | NO MEETING
October 13th, 2024 | 1:00pm - 1:15pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Backend and frontend updates | We reviewed the new backend endpoints for fetching course data and discussed updates to the teams page. We also reviewed the pull request process to confirm alignment with project requirements and discussed future improvements for smoother integration.
October 14th-15th, 2024 | 30 minutes | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Instructor’s student list 2) CSV upload page | We discussed the design and implementation plan for the instructor's student list and reviewed the frontend interface for the CSV upload page. Team members shared insights on database rules to enforce team restrictions, which we agreed to implement in the upcoming days.
October 16th-17th, 2024 | 30 minutes | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Course selection 2) Team CRUD | We discussed the development of the course selection functionality, with an emphasis on improving user experience. Team members also reviewed the current status of the team CRUD operations, shared feedback on acceptance testing, and brainstormed UI improvements for teammate evaluation.
October 18th, 2024 | 10:00am - 10:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) API learning 2) UI design for team creation | The team explored strategies for integrating APIs effectively. We also reviewed the current design for the team creation page and discussed adjustments to improve clarity and usability.
October 19th, 2024 | 4:15pm - 4:30pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Pull request merging 2) Test fixes | We discussed the strategy for merging pull requests, including handling conflicts and managing test fixes. Team members shared insights on efficient testing practices, which will streamline the integration process.
October 20th, 2024 | NO MEETING
October 21st, 2024 | 11:00am-11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Team creation page 2) CI pipeline debugging | We discussed the final adjustments needed for the team creation page and reviewed issues with the CI pipeline, proposing debugging steps to improve stability for ongoing development.
October 22nd-23rd, 2024 | 30 minutes | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Evaluations endpoints 2) Members page implementation | The team discussed the requirements for the evaluations endpoints and reviewed their integration with the frontend. We also examined the remaining steps for the members page implementation and proposed final modifications for the CSV upload functionality.
October 24th, 2024 | 4:20pm - 4:35pm | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Task separation and sprint planning 2) Commitment review 3) Task timing and context usage | In this meeting, we discussed the current task assignments and reviewed our commitments for the end of the sprint. We shared our thoughts on task timing and agreed on adjustments to ensure deadlines were realistic. We also explored how to best use the context to streamline task management and keep grading expectations in mind.
October 25th, 2024 | 1:15pm - 1:30pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Meeting minutes review 2) Context implementation for teacher view | The team focused on going over the meeting minutes to ensure accurate documentation of key points. We also discussed the use of context in the Members page for the teacher view, reviewing the implementation to make sure it aligned with project requirements and user experience expectations.
October 26th, 2024 | 11:00am - 11:15am | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) CSV file upload improvements 2) Data transmission to API | We reviewed the CSV file upload feature and discussed improvements to ensure data transmitted effectively to the API. Team members shared insights on optimizing the upload function and strategies to enhance accuracy. Error handling was also reviewed to make sure that data integrity was maintained across uploads.
October 27th, 2024 |  |  | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi |  |  | Mauricio has a hackathon