## Feuil1
Daily Scrum | Time | Location | Attendees | Agenda | Discussion | Important note
November 6, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1) Learn Cypress testing framework | The team focused on learning Cypress as a tool to aid in their testing processes.
November 7, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1) Review task progress 2) Debug and pair program on tasks 3) Discuss next steps and project progress | The team discussed their current task progress, debugged code issues together, and participated in pair programming sessions to enhance efficiency. They also reviewed the next steps and discussed the overall progress of the project.
November 8, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1) Continue Cypress learning 2) Work on Cypress register test 3) Meet to discuss the register test specifics | Team members made progress in learning Cypress and focused on working with the Cypress register test. Mauricio and another team member met to discuss this register test in detail to refine its implementation.
November 9, 2024 | 11:30 to 11:45 AM | Concordia University H8 Lab Room | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1) Continue "Create Teams" feature implementation 2) Debug CSS issues 3) Continue learning Cypress 4) Develop email module and Peer Check email API | Team members continued implementing the "Create Teams" feature, worked on debugging CSS, and started familiarizing themselves further with Cypress. Additionally, a module was created to email users, and an API for Peer Check emails was developed using Gmail.
November 10, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1) Conduct acceptance testing 2) Review pull requests 3) Continue Cypress learning 4) Update team documentation | The team focused on acceptance testing and reviewed pull requests. They continued their work on Cypress and made updates to team documentation to ensure alignment on testing processes.