## Feuil1
Daily Scrum | Time | Location | Attendees | Agenda | Discussion
October 3rd, 2024 | 4:15pm - 4:30pm | Concordia University H8 Lab Room | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Go over user stories and tasks | During this meeting, we reviewed the user stories and tasks currently in progress. We ensured that each team member had a clear understanding of their responsibilities and the next steps for the project.
October 5th, 2024 | 11:00pm - 11:15:pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Input validation 2) Table creation for courses and teams | In this meeting, we focused on updating the input validation for account creation on both the frontend and backend. Additionally, we created a table for courses and updated the functionality so that teams could be attached to a course, streamlining the data structure for future use.
October 9th, 2024 | 11:00pm - 11:15:pm | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi | 1) Fetch module clarification 2) Project modifications | We discussed the fetch module and clarified its usage within the project. Additionally, we decided to remove the username field from the project as it was no longer necessary based on the updated requirements.
|  | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi
|  | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi
|  | Discord | Mauricio Murillo, Rym Dallali, Nolan Ganz, Khalil Labban, Jaden Wright-Maurais, Carla Chamandi