## Feuil1
Daily Scrum | Time | Location | Attendees | Agenda | Discussion | Important note
November 6, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Learn Cypress. | The team focused on learning how to use Cypress, familiarizing themselves with its features and setup.
November 7, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Discuss task progress. ~Debug code. ~Pair programming. ~Plan the next steps for the project. | Team members provided updates on their tasks, debugged parts of the code collaboratively, and participated in pair programming. They also discussed the project’s next steps and evaluated its current progress.
November 8, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Work on Cypress tests. ~Meet with Mauricio to discuss the register test. | The team continued working on Cypress and specifically focused on the register test. A meeting with Mauricio provided guidance on refining the test.
November 9, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Continue CreateTeams implementation. ~Debug CSS. ~Start learning Cypress. | The team made progress on the CreateTeams implementation, resolved CSS issues, and began exploring Cypress testing.
November 10, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Complete acceptance tests. ~Learn Cypress. ~Review pull requests. ~Work on team documentation. | The team finalized acceptance tests, expanded their knowledge of Cypress, and reviewed pull requests. Team documentation was also updated.
November 13, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Review pull requests. ~Create UI for email notification. ~Sprint planning tasks. | Pull requests were reviewed, and a UI for email notifications was designed. The team also planned tasks for the sprint and addressed Cypress test fixes for user login and registration.
November 14, 2024 | 4:15 to 5:55 AM | Concordia University H8 Lab Room | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Finish fixing Cypress test for user register. | The team resolved issues in the Cypress test for user registration, completing the task successfully.
November 19, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Conduct research on Electron app development. | Research on Electron app development was conducted to understand its potential application in the project.
November 21, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Research Cypress node modules. ~Add database queries in Cypress. ~Create user stories for Sprint 4. | Research was conducted on using node modules in Cypress, database queries were added, and user stories for Sprint 4 were drafted collaboratively.
November 22, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Work on Cypress tests (see results and reviewing teammates). ~Create endpoints for uploading files. ~Review pull requests. | The team worked on various Cypress tests, developed file upload endpoints, and reviewed pull requests to ensure code quality.
November 23, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Develop Cypress tests for CSV upload. ~Work on presentation slides. ~Make endpoints for downloading files and anonymized feedback. | Cypress tests were created for CSV uploads, and presentation slides were prepared. Additionally, the backend functionality for downloading files and releasing anonymized feedback was implemented.
November 24, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Debug Cypress tests. ~Refactor components for document uploading and downloading. ~Fix minor bugs. ~Work on team documentation. | The team debugged Cypress tests, refined document management components, and fixed minor issues. Updates were also made to the team documentation.
November 25, 2024 | 4:15 to 5:55 AM | Concordia University H8 Lab Room | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Implement UI for students to view their reviews. ~Complete Cypress tests for document uploads. ~Review pull requests. ~Create a static analysis pipeline. | The team developed a UI for students to view their reviews and completed Cypress tests for document uploads. Pull requests were reviewed, and a static analysis pipeline was created to improve code quality.
November 26, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali Mauricio Murillo Jaden Wright-Maurais Khalil Labban Carla Chamandi Nolan Ganz | ~Finalize Cypress tests. ~Review pull requests. ~Fix bugs. ~Create a static analysis pipeline. ~Prepare presentation slides. ~Record a video overview of the website. | The team finalized Cypress tests, reviewed pull requests, and fixed bugs in the project. They also refined the static analysis pipeline, prepared presentation slides, and recorded a video overview of the website to highlight project features.