## Feuil1
Daily Scrum | Time | Location | Attendees | Agenda | Discussion | Important note
October 30, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Review PR 2. Finalize CVS upload page 3. Debug code | The team reviewed pull requests and made progress in debugging issues within the code. Additionally, the final design of the CVS upload page was discussed and worked on.
October 31, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Update side menu CSS 2. Highlight current selected course 3. Fix redirection bug 4. Review PR 5. Discuss unit and integration testing 6. Plan user stories | The team updated the side menu's CSS, added functionality to highlight the selected course, and worked on fixing a redirection bug. They also reviewed pull requests and discussed plans for unit and integration testing. The team drafted user stories and talked about acceptance testing requirements.
November 1, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Review PRs 2. Fix minor bugs | Pull requests were reviewed, and minor bugs were identified and fixed as part of the ongoing sprint tasks.
November 2, 2024 | 11:30 to 11:45 AM | Concordia University H8 Lab Room | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Work on UI design for result view 2. Implement summary endpoints 3. Research on Jest | The team worked on the UI design for the result view from the Instructor's perspective and implemented endpoints for summarizing evaluations. Some team members also researched Jest for potential testing purposes.
November 3, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Continue UI design for result view 2. Develop tests for summary endpoints | The result view UI design was refined further, and tests were created for the summary of evaluations endpoint.
November 4, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Make changes based on PR feedback 2. Work on detailed view PR | The team reviewed the summary PR and incorporated feedback. They also began working on the detailed view PR.
November 5, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Implement UI and functionality for evaluation results dashboard 2. Begin detailed view of evaluation results 3. Confirm Cypress usage | The UI and functionality for the evaluation results dashboard were implemented, and work began on the detailed view for evaluation results. The team also confirmed that Cypress would be used for testing.
November 6, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Work on detailed view implementation 2. Conduct PR reviews 3. Learn Cypress | Progress was made on implementing the detailed view of evaluation results, and pull requests were reviewed. Team members continued learning Cypress to implement test automation.
November 7, 2024 | 4:15 to 5:55 PM | Concordia University H8 Lab Room | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Review task progress 2. Debug code 3. Continue Cypress learning | The team discussed their current task progress, debugged some issues, and participated in pair coding sessions. They also outlined the next steps for the project, and several members focused on learning Cypress and creating related tests.
November 8, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Develop Cypress register test 2. Meet to discuss register test | The register test was worked on in Cypress, and a meeting was held to discuss its implementation in detail.
November 9, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Continue createTeams implementation 2. Develop module for emailing users | Progress continued on implementing the createTeams feature, and a module for sending emails to users was created, along with a Peer Check email API.
November 10, 2024 | 11:30 to 11:45 AM | Discord | Rym Dallali, Mauricio Murillo, Jaden Wright-Maurais, Khalil Labban, Carla Chamandi, Nolan Ganz | 1. Finish acceptance tests 2. Review PRs 3. Work on team documentation | The team completed acceptance tests, reviewed outstanding pull requests, and worked on documenting aspects of the project related to team operations and processes.